## Slide 1: Container Proofs of Concept

## Slide 2: A Quick Refresher
More efficient usage of server resources
Rapid deployments
Simplicity
Security
Rapid iteration for dev teams

## Slide 3: Why Now?
We know containers are coming
We want to manage one consistent platform
We want a ready answer for people
Notes: In fact, we have containers in house today, but we don’t have a long-term plan to manage them for everyone.

## Slide 4: Three Phases
Phase One: Proofs of concept (This conversation)
Phase Two: Basic Container Support
Phase Three: DevOps Integration
Notes: POCs – we’re really talking about making sure the vendors we’re considering are ready for prime time.

## Slide 5: The Players
Owner: Technical Architecture Group
Driver: Eric Burcham
Core Team: Eric Burcham, Dylan Clark, Mike Bollman, Lowell Roberts, Stuart Wagner
Stakeholders: Big Data, Desktop Support, Development Managers, eBusiness, Engineering, Network Team, NOC, Oracle Team, SCADA, Security and Compliance, Server Team
Vendors: Docker Enterprise, Red Hat OpenShift, Rancher
Notes: Core Team – Will be doing or managing the work
Stakeholders – Wil be consulted during the POC planning phase for their input, and will have an opportunity to get their hands on the environments.
Vendors – Of the vendors in the market, we talked to many and think these three have the most mature offerings

## Slide 6: Phase One (2 Months)
Proofs of Concept, Cost Analysis, and Vendor Selection
Notes: I feel pretty good about this estimate.
This time should mostly be spent planning, and waiting for vendors
We have had demos with various vendors
We have expressed concerns about security, copy control, license management, etc…
Vendors have addressed those concerns verbally
We want those solutions demonstrated
We want to get our hands on the solutions
We want to get pricing
We want to get SLAs
We want to understand consulting costs

## Slide 7: Proofs of Concept
Present requirements
Demonstrations
Formal pricing
Notes: - Requirements -
For objectivity we’ll present identical requirements to each vendor
We will provide answers to questions to all vendors
We’ll provide the application so they can’t use a canned example
- Demonstrations -
We want them to do the demo on our infrastructure
We want to keep the environments around for awhile
We’ll give environment access to our current container users
We’ll try to get this done for free
- Pricing -
Application pricing
Hardware requirements

## Slide 8: POC Scope
Automatic Scaling
Authentication / Authorization
Clustering
Copy Control
Deployment
Desktop Support
Health Monitoring
High Availability
Log Management
Management
Network Isolation for Testing
Orchestration
Resource Allocation
Security
Budgeting
Change Management
Desktop Host Management
Image Approval and Management
Licensing and Compliance
Long-term viability
Resource Planning
Security Audits
Technical Support Quality and Availability

## Slide 9: Phase One Outcome
We select a primary vendor
We have faith in the solution
We understand pricing and support
Notes: We understand how our requirements our met
Our teams have had their hands on the solutions
We can better estimate phases two and three

## Slide 10: Phase Two (2 Months)
Basic Container Support
Notes: This is a rough time estimate. We’ll tighten it up after phase one.
We can run pre-built containers provided by vendors.
We can run our own containerized applications.
Deployments and configuration handled manually.

## Slide 11: Phase Two Outcome
Licensing and support agreements
We know how containers are internally paid for
Security and compliance review
Physical infrastructure is allocated
NOC integration is complete
Personnel are ready

## Slide 12: Phase Three (2 – 6 Months)
DevOps Integration
Notes: This is a VERY rough time estimate
There may be significant costs
We’re pretty busy, so we expect to engage a vendor to do this

## Slide 13: Phase Three Outcome
Desktop container support
Boilerplate for common project types
Continuous integration
Automated deployments
Notes: Push people into the pit of success

## Slide 14: Containers as a Service
Code
Debug
Run
Validate
Private
Container
Registry
Source Control
Build
Verify
Container Hosts
Desktop
Test Env
UAT Env
On-Premise
Off-Premise
Notes: Add detailed notes about why this takes so long.

## Slide 15: Next Steps
Finalize our team
Visit with all stakeholders
Write our RFP document
Submit RFP to vendors
Coordinate vendor presentations